## cytori therapeutics inc
Cytori Therapeutics INC
Exhibit No. |  | Description
| 10.9 | Contract HHSO100201200008C dated September 27, 2012, by and between the Company and the U.S. Department of Health and Human Services Biomedical Advanced Research and Development Authority (portions of the exhibit have been omitted pursuant to a request for confidential treatment).

## cytori therapeutics inc-1
CYTORI THERAPEUTICS, INC.
Date: October 3, 2012 | By: /s/ Mark E. Saad
Mark E. Saad
Chief Financial Officer

## cytori therapeutics inc-2
Cytori Therapeutics INC
Base Period |  |  | 9/28/12 to 9/27/14
Name | WBS Number |  | Start Date | Finish/Due Date | Deliverable
Technical and Project Management |  | 1.1.1.4 | 9/28/2012 | 10/22/2012 | Updated Task/Deliverables List
Hiring: Base Period |  | 1.1.1.5 | 10/2/2012 | 1/22/2013 | Include in the applicable monthly report
Subcontractor Management |  | 1.1.2 | 10/16/2012 | 1/7/2013 | Subcontractor Management Plan
Risk Management |  | 1.1.3.3 | 10/16/2012 | 3/11/2013 | Risk Management Plan
EVMS: Implementation Plan |  | 1.1.4.2 | 10/15/2012 | 3/24/2013 | EVMS Systems Plan
EVMS: Implementation |  | 1.1.4.4 | 3/24/2013 | 7/24/2013 | EVMS Systems Report
Preclinical Studies: Multiple Final Reports |  | 1.3.1.3.16 | 10/2/2012 | 5/5/2014 | Final report submitted to and accepted by BARDA CO/COR
Human Preclinical Studies Report |  | 1.3.2.1 | 9/28/2012 | 2/24/2014 | Final report submitted to and accepted by BARDA CO/COR
Pilot Clinical Trial Clinical Protocol Draft Development Plan |  | 1.4.1.3 | 9/5/2013 | 10/18/2013 | Draft or Outline Clinical Protocol submitted to BARDA CO/COR approval
*** |  | 1.5.1.2 | 12/9/2013 | 12/9/2013 | Meeting minutes
*** |  | 1.6.1 | 10/30/2012 | 8/19/2013 | Final report submitted to and accepted by BARDA CO/COR
*** |  | 1.6.2 | 11/27/2012 | 8/5/2013 | Final report submitted to and accepted by BARDA CO/COR

## cytori therapeutics inc-3
Option 1: Pilot Clinical Study |  | 9/28/2013 to 9/27/16
Name |  | Start Date | Finish Date | Deliverable
Clinical Hiring | 1.1.1.6.1 | 3/19/2014 | 7/8/2014 | Include in the applicable bi-monthly report
Development Hiring | 1.1.1.6.2 | 3/19/2014 | 5/20/2014 | Include in the applicable bi-monthly report
*** Feasability Final Report | 1.3.1.4.1 | 3/19/2014 | 1/21/2015 | Final report submitted to and accepted by BARDA CO/COR
*** Final Report | 1.3.1.4.2 | 3/19/2014 | 10/22/2014 | Final report submitted to and accepted by BARDA CO/COR
*** Final Report | 1.3.1.4.3 | 5/1/2014 | 7/29/2015 | Final report submitted to and accepted by BARDA CO/COR
*** Final Report | 1.3.2.3.1 | 3/19/2014 | 9/18/2014 | Final report submitted to and accepted by BARDA CO/COR
*** Final Report | 1.3.2.3.2 | 3/19/2014 | 9/8/2014 | Final report submitted to and accepted by BARDA CO/COR
*** Final Report | 1.3.2.4 | 3/19/2014 | 7/14/2014 | Final report submitted to and accepted by BARDA CO/COR
*** Final Report | 1.3.2.5 | 4/4/2014 | 11/19/2014 | Final report submitted to and accepted by BARDA CO/COR
*** Final Report | 1.4.1.4 | 3/19/2014 | 12/11/2015 | Final report submitted to and accepted by BARDA CO/COR
*** Protocol Development Submission | 1.4.2.1 | 3/23/2015 | 4/10/2015 | Protocol submitted to and accepted by BARDA CO/COR
*** | 1.5.1.6 | 10/27/2014 | 10/27/2014 | ***
*** Report | 1.6.3.1 | 3/9/2014 | 4/22/2014 | Interim Report
*** Report | 1.6.3.2 | 3/9/2014 | 8/5/2014 | Interim Report
*** Final Report | 1.6.3.3 | 8/6/2014 | 9/17/2014 | Final report submitted to and accepted by BARDA CO/COR

## cytori therapeutics inc-4
Option 2: Pivotal Clinical Trial |  | 9/28/14 to 9/27/17
Name |  | Start Date | Finish Date | Deliverable
Clinical Hiring | 1.1.1.7 | 6/2/2015 | 8/10/2015 | Include in the applicable bi-monthly report
*** Interim Report | 1.4.2.4 | 2/12/2016 | 2/12/2016 | ***
Study Complete Final Report | 1.4.2.10 | 6/1/2017 | 6/1/2017 | Final report submitted to and accepted by BARDA CO/COR
*** | 1.5.3.2 | 6/1/2017 | 6/1/2017 | ***
*** | 1.5.3.3 | 9/21/2017 | 9/21/2017 | ***
Option 3: Comb. Inj. Treatment Optimization |  | 9/28/13 to 9/27/17
Name |  | Start Date | Finish Date | Deliverable
Clinical Hiring | 1.1.1.8 | 6/3/2016 | 7/14/2016 | Include in the applicable bi-monthly report
Research and Development Hiring | 1.1.1.9 | 3/19/2014 | 5/27/2014 | Include in the applicable bi-monthly report
*** Studies Final Report | 1.3.1.5 | 3/19/2014 | 1/25/2017 | Final report submitted to and accepted by BARDA CO/COR
*** Final Report | 1.3.2.2 | 3/9/2014 | 8/19/2014 | Final report submitted to and accepted by BARDA CO/COR
*** Final Report | 1.4.3 | 1/13/2016 | 5/10/2017 | Final report submitted to and accepted by BARDA CO/COR
*** | 1.5.4 | 4/27/2017 | 8/30/2017 | ***
*** Final Report | 1.6.4 | 9/16/2015 | 5/22/2017 | Final report submitted to and accepted by BARDA CO/COR

## cytori therapeutics inc-5
FARCLAUSE NO. |  | DATE | TITLE
| 52.202-1 | Jan 2012 | Definitions (Over the Simplified Acquisition Threshold)
| 52.203-3 | Apr 1984 | Gratuities (Over the Simplified Acquisition Threshold)
| 52.203-5 | Apr 1984 | Covenant Against Contingent Fees (Over the Simplified Acquisition Threshold)
| 52.203-6 | Sep 2006 | Restrictions on Subcontractor Sales to the Government (Over the Simplified Acquisition Threshold)
| 52.203-7 | Oct 2010 | Anti-Kickback Procedures (Over the Simplified Acquisition Threshold)
| 52.203-8 | Jan 1997 | Cancellation, Rescission, and Recovery of Funds for Illegal or Improper Activity (Over the Simplified Acquisition Threshold)
| 52.203-10 | Jan 1997 | Price or Fee Adjustment for Illegal or Improper Activity (Over the Simplified Acquisition Threshold)
| 52.203-12 | Oct 2010 | Limitation on Payments to Influence Certain Federal Transactions (Over $150,000)
| 52.204-4 | May 2011 | Printed or Copied Double-Sided on Postconsumer Fiber Content Paper(Over the Simplified Acquisition Threshold)
| 52.204-7 | Feb 2012 | Central Contractor Registration
| 52.204-10 | Feb 2012 | Reporting Executive Compensation and First-Tier Subcontract Awards ($25,000 or more)
| 52.209-6 | Dec 2010 | Protecting the Government's Interests When Subcontracting With Contractors Debarred, Suspended, or Proposed for Debarment (Over $30,000)
| 52.215-2 | Oct 2010 | Audit and Records - Negotiation [Note: Applies to ALL contracts funded in whole or in part with Recovery Act funds, regardless of dollar value, AND contracts over the Simplified Acquisition Threshold funded exclusively with non-Recovery Act funds.]
| 52.215-8 | Oct 1997 | Order of Precedence - Uniform Contract Format

## cytori therapeutics inc-6
52.215-10 | Aug 2011 | Price Reduction for Defective Certified Cost or Pricing Data (Over $700,000)
52.215-12 | Oct 2010 | Subcontractor Cost or Pricing Data (Over $700,000)
52.215-14 | Oct 2010 | Integrity of Unit Prices (Over the Simplified Acquisition Threshold)
52.215-15 | Oct 2010 | Pension Adjustments and Asset Reversions (Over $700,000)
52.215-18 | Jul 2005 | Reversion or Adjustment of Plans for Post-Retirement Benefits (PRB) other than Pensions
52.215-19 | Oct 1997 | Notification of Ownership Changes
52.215-21 | Oct 2010 | Requirements for Certified Cost or Pricing Data and Data Other Than Certified Cost or Pricing Data - Modifications
52.215-22 | Oct 2009 | Limitations on Pass-Through Charges – Identification of Subcontract Effort
52.215-23 | Oct 2009 | Limitations on Pass-Through Charges (Over the Simplified Acquisition Threshold)
52.216-7 | Jun 2011 | Allowable Cost and Payment
52.216-8 | Jun 2011 | Fixed Fee
52.219-8 | Jan 2011 | Utilization of Small Business Concerns (Over the Simplified Acquisition Threshold)
52.219-9 | Jan 2011 | Small Business Subcontracting Plan (Over $650,000, $1.5 million for Construction)
52.219-16 | Jan 1999 | Liquidated Damages - Subcontracting Plan (Over $650,000, $1.5 million for Construction)
52.222-2 | Jul 1990 | Payment for Overtime Premium (Over the Simplified Acquisition Threshold) (Note: The dollar amount in paragraph (a) of this clause is $0 unless otherwise specified in the contract.)
52.222-3 | Jun 2003 | Convict Labor
52.222-19 | Mar 2012 | Child Labor – Cooperation with Authorities and Remedies
52.222-21 | Feb 1999 | Prohibition of Segregated Facilities
52.222-26 | Mar 2007 | Equal Opportunity
52.222-35 | Sep 2010 | Equal Opportunity for Veterans ($100,000 or more)
52.222-36 | Oct 2010 | Affirmative Action for Workers with Disabilities
52.222-37 | Sep 2010 | Employment Reports on Veterans ($100,000 or more)
52.222-40 | Dec 2010 | Notification of Employee Rights Under the National Labor Relations Act (Over the Simplified Acquisition Threshold)
52.222-50 | Feb 2009 | Combating Trafficking in Persons

## cytori therapeutics inc-7
52.222-54 | Jan 2009 | Employment Eligibility Verification (Over the Simplified Acquisition Threshold)
52.223-6 | May 2001 | Drug-Free Workplace
52.223-18 | Aug 2011 | Encouraging Contractor Policies to Ban Text Messaging While Driving
52.225-1 | Feb 2009 | Buy American Act - Supplies
52.225-13 | Jun 2008 | Restrictions on Certain Foreign Purchases
52.225-25 | Nov 2011 | Prohibition on Contracting with Entities Engaging in Sanctioned Activities Related to Iran – Representation and Certification
52.227-1 | Dec 2007 | Authorization and Consent, Alternate I (Apr 1984)
52.227-2 | Dec 2007 | Notice and Assistance Regarding Patent and Copyright Infringement
52.227-11 | Dec 2007 | Patent Rights — Ownership by the Contractor (Note: In accordance with FAR 27.303(b)(2), paragraph (e) is modified to include the requirements in FAR 27.303(b)(2)(i) through (iv). The frequency of reporting in (i) is annual.
52.227-14 | Dec 2007 | Rights in Data — General
52.227-16 | Jun 1987 | Additional Data Requirements
52.232-9 | Apr 1984 | Limitation on Withholding of Payments
52.232-17 | Oct 2010 | Interest (Over the Simplified Acquisition Threshold)
52.232-20 | Apr 1984 | Limitation of Cost
52.232-23 | Jan 1986 | Assignment of Claims
52.232-25 | Oct 2008 | Prompt Payment, Alternate I (Feb 2002)
52.232-33 | Oct 2003 | Payment by Electronic Funds Transfer—Central Contractor Registration
52.233-1 | Jul 2002 | Disputes
52.233-2 | Sep 2006 | Service of Protest
52.233-3 | Aug 1996 | Protest After Award, Alternate I (Jun 1985)
52.233-4 | Oct 2004 | Applicable Law for Breach of Contract Claim
52.242-1 | Apr 1984 | Notice of Intent to Disallow Costs
52.242-3 | May 2001 | Penalties for Unallowable Costs (Over $700,000)
52.242-4 | Jan 1997 | Certification of Final Indirect Costs

## cytori therapeutics inc-8
52.242-13 | Jul 1995 | Bankruptcy (Over the Simplified Acquisition Threshold)
52.242-15 | Aug 1989 | Stop Work Order
52.243-2 | Aug 1987 | Changes - Cost Reimbursement, Alternate V (Apr 1984)
52.244-2 | Oct 2010 | Subcontracts (Over the Simplified Acquisition Threshold), Alternate I (June 2007)
52.244-5 | Dec 1996 | Competition in Subcontracting (Over the Simplified Acquisition Threshold)
52.244-6 | Dec 2010 | Subcontracts for Commercial Items
52.245-1 | Apr 2012 | Government Property
52.245-9 | Apr 2012 | Use and Charges
52.246-9 | Apr 1984 | Inspection of Research and Development (Short Form)
52.246-23 | Feb 1997 | Limitation of Liability (Over the Simplified Acquisition Threshold)
52.247-34 | Nov 1991 | FOB Destination
52.247-63 | Jun 2003 | Preference for US Flag Air Carriers
52.249-6 | May 2004 | Termination (Cost-Reimbursement)
52.249-14 | Apr 1984 | Excusable Delays
52.251-1 | Apr 2012 | Government Supply Sources
52.253-1 | Jan 1991 | Computer Generated Forms

## cytori therapeutics inc-9
HHSARCLAUSE NO. |  | DATE | TITLE
| 352.201-70 | Jan 2006 | Paperwork Reduction Act
| 352.202-1 | Jan 2006 | Definitions - with Alternate paragraph (h) (Jan 2006)
| 352.203-70 | Mar 2012 | Anti-Lobbying
| 352.216-70 | Jan 2006 | Additional Cost Principles
| 352.222-70 | Jan 2010 | Contractor Cooperation in Equal Employment Opportunity Investigations
| 352.223-70 | Jan 2006 | Safety and Health
| 352.224-70 | Jan 2006 | Privacy Act
| 352.227-70 | Jan 2006 | Publications and Publicity
| 352.228-7 | Dec 1991 | Insurance – Liability to Third Persons
| 352.231-71 | Jan 2001 | Pricing of Adjustments
| 352.233-71 | Jan 2006 | Litigation and Claims
| 352.242-70 | Jan 2006 | Key Personnel
| 352.242-73 | Jan 2006 | Withholding of Contract Payments
| 352.242-74 | Apr 1984 | Final Decisions on Audit Findings
| 352.270-4 | Jan 2006 | Protection of Human Subjects
| 352.270-6 | Jan 2006 | Restrictions on Use of Human Subjects